## Slide 1: CAPA
How To Write a Simple and Effective CAPA Plan

## Slide 2: CAPA
CAPA PLAN
What is the difference between CAP and CAPA?
CAP=Corrective Action Plan
CAPA=Corrective Action and Preventive Action Plan

## Slide 3: Who needs a CAPA?
If you personally make a mistake more than once
If you identify a pattern of errors
If a procedure consistently fails
Retraining is not working
Your study participants are constantly non-complaint

## Slide 4: 8 Steps of a CAPA Plan
Identify an issue
Define the root cause of the issue
Correct the issue
Develop a plan to prevent the issue from reoccurring
Implement the plan to prevent the issue
Follow-up on and evaluate the plan implemented
Repeat as necessary
Document closure

## Slide 5: Writing a Procedure
Objective: address and correct current issue and prevent future similar issues from occurring
Identify the W’s and one H
Who
What
When
Where
How

## Slide 6: CAPA Plan Form
Corrective Action
What is the issue
Why is there an issue
How will the issue be corrected
When was the correction made
Who was involved in the correction
Document resolution

## Slide 7: CAPA Plan Form
Preventive Action
What is the issue
Why is there an issue
What is the plan to prevent the issue in the future
When and How will the plan be implemented
When and How will the plan be evaluated
Documented resolution

## Slide 8: CAPA Implementation
Implementing a CAPA Plan
Corrective Action
Communicate
Educate
Correct
Document
Preventive Action
Communicate
Educate
Implement
Evaluate
Document

## Slide 9: Final Thoughts
Do not be afraid to use a CAPA plan
Revisit your CAPA Plan
Own your improvement process