| Pre-Study Task | PI | Study Coordinator | Regulatory Coordinator | <<Add Role>> | <<Add Role>> | NOTES |
| --- | --- | --- | --- | --- | --- | --- |
| Submit Confidentiality Disclosure Agreement (CDA) to Office of Sponsored Programs (OSP) |  |  |  |  |  |  |
| Complete UAB Protocol Feasibility Assessment Form (See Clinical Trials Kiosk – Investigator Toolkit or use site’s own feasibility assessment form) |  |  |  |  |  |  |
| Complete UAB Recruitment and Retention Plan Worksheet (See Clinical Trials Kiosk – Investigator Toolkit) |  |  |  |  |  |  |
| IRAP Project Registration/Single Identifier |  |  |  |  |  |  |
| OCS-CCTS-CBR Submission (if yes to any questions below) - Will the study involve UAB Health System clinical billable services? - Is study be managed in OnCore? - Will study use CCTS Clinical Services? |  |  |  |  |  |  |
| Develop and Negotiate budget (See Clinical Trials Kiosk – Clinical Trials Budget Tools and Workshop) |  |  |  |  |  |  |
| Pre-Study | PI | Study coordinator | Regulatory | Manager/Administrator | Pharmacy | NOTES |
| Submit Clinical Trial Agreement (CTA) & other required documents to OSP |  |  |  |  |  |  |
| Regulatory (See Clinical Trials Kiosk – Regulatory Coordinator Toolkit) - Complete Site Contact Sheet - Receive start-up packet from Sponsor/CRO (typically includes protocol, PSP, ICF, logs, recruitment materials, some essential documents, etc.) - Start and maintain ISF - Collect and maintain essential documents - IRB submissions |  |  |  |  |  |  |
| Create Study Contacts and Vendors List (See Clinical Trials Kiosk – All Tools and Templates) - Study Staff - Ancillary Staff - Vendors - Lab, EDC, IWRS - Electronic devices - ECG, Radiology, etc. transmission - Safety Reports - Home/telehealth services - Other |  |  |  |  |  |  |
| Pre-Study | PI | Study coordinator | Regulatory | Manager/Administrator | Pharmacy | NOTES |
| Map out plans - Space - Logistics - Special considerations |  |  |  |  |  |  |
| Validate OnCore Calendar |  |  |  |  |  |  |
| Submit PowerTrials Study Summary |  |  |  |  |  |  |
| Validate PowerPlan |  |  |  |  |  |  |
| Greenphire set-up and obtain UAB ClinCards |  |  |  |  |  |  |
| Enter budget in Oncore (Required for Industry Trials March 1, 2024. See Clinical Trials Kiosk – Oncore Financials) |  |  |  |  |  |  |
| Supplies & equipment - Make list - Place orders, if needed - Perform inventory checks throughout startup period |  |  |  |  |  | Remember, lab supplies may expire while waiting on study to open |
| Create source docs (See Clinical Trials Kiosk – Study Coordinator Toolkit) |  |  |  |  |  |  |
| Make subject binders |  |  |  |  |  |  |
| Complete required trainings |  |  |  |  |  | Training logs filed in ISF. |
| Pre-Study | PI | Study coordinator | Regulatory | Manager/Administrator | Pharmacy | NOTES |
| Recruitment - Distribute recruitment materials - Create recruitment log (See Clinical Trials Kiosk – Study Coordinator Toolkit) |  |  |  |  |  | Recruitment materials must have IRB approval. |
| Schedule SIV |  |  |  |  |  |  |
| Attend SIV |  |  |  |  |  |  |
| Schedule internal study initiation meeting |  |  |  |  |  | Have a team meeting prior to scheduling first screen to ensure everyone on the same page. (Or include as part of staff meeting) |
| Engage clinic staff (MD, physician extenders, nurses) - Provide eligibility criteria - Keep ongoing list of potential participants |  |  |  |  |  |  |
| Conduct mock visit |  |  |  |  |  |  |